## Project roles summary
Role | Name | School/Unit | Email | Phone | Mobile | Appointed by | Date
Project level roles
Business sponsor | Niall Scott | Corporate Communications |  |  |  | DCPB
Business visionary | [5 empty] | DCPB
Project manager | Gareth Saunders | Digital communications |  |  |  | DCPB
| Carley Hollis | Digital communications |  |  |  | DCPB
Technical coordinator (dev) | Steve Evans | Digital communications |  |  |  | Project manager
Technical coordinator (content) | Carley Hollis | Digital communications |  |  |  | Project manager
Solutions development team roles
Business ambassador
Business analyst | Gareth Saunders | Digital communications |  |  |  | DCPB
Team leader | Steve Evans | Digital communications |  |  |  | DCT
Solution developer (content) | Jenny Hamrick | Digital communications |  |  |  | DCT
| John Chapman | Digital communications |  |  |  | DCT
| Maria Drummond | Digital communications |  |  |  | DCT
Solution developer (design) | Lewis Wake | Digital communications |  |  |  | DCT
Solution developer (dev) | Duncan Sanderson | Digital communications |  |  |  | DCT
| Nick Mullen | Digital communications |  |  |  | DCT
| Peter Woodbridge | Digital communications |  |  |  | DCT
| Steve Evans | Digital communications |  |  |  | DCT
Solution testers | Carley Hollis | Digital communications |  |  |  | DCT
| Duncan Sanderson | Digital communications |  |  |  | DCT
| Gareth Saunders | Digital communications |  |  |  | DCT
| Jenny Hamrick | Digital communications |  |  |  | DCT
| John Chapman | Digital communications |  |  |  | DCT
| Lewis Wake | Digital communications |  |  |  | DCT
| Maria Drummond | Digital communications |  |  |  | DCT
| Nick Mullen | Digital communications |  |  |  | DCT
| Peter Woodbridge | Digital communications |  |  |  | DCT
| Steve Evans | Digital communications |  |  |  | DCT
Supporting roles
Business advisors
Technical advisor

## Communications log
Sprint (number and name) | Date (yyyy-mm-dd) | Person(s) contacted | Email address | Telephone | Reason | How contacted | Notes | Contact by whom | Action/notes

## Change log
Sprint (number and name) | ID | Prosposed change | Name of proposer | Why is this change required? | Date change needs to be accepted by | Impact of change (low/medium/high) | Authorised by | Date of authorisation | Next action | Current status (in review, accepted, rejected, closed) | Notes | Impact of change

## Incidents log
Sprint | Date (yyyy-mm-dd) | Incident | Raised by? | Date issue needs to be resolved by | Impact of issue (low/medium/high) | Next action | Current status (in review, accepted, rejected, closed) | Authorised by | Date of authorisation | Added to risk log? | Notes

## Risk log
Ref. | Description (IF...) | Category | DSDM Phase | Date captured | Impact (1–3) | Likelihood (1—5) | Risk score | Owner | Action required to mitigate against (THEN...) | Action required to resolve (ELSE...) | Resolution due date | Added by | Notes
1 |  |  |  |  | 1 | 1 | 1
2 |  |  |  |  | 2 | 3 | 6
3 |  |  |  |  | 3 | 5 | 15
4 | [6 empty] | 0
0
0
0
0
0
0
Notes
Ref.
Sequential reference number (unique identifier) so that risks can be referenced. (If you remove risks from the list do not renumber the remaining risks.)
Description
Identify sources of risk. Do not worry when you find risks—project management is largely about risk management.
Project definition (objectives, scope, requirements)
Business case
Budget
Support for the project
Expectations
Plan (estimates, schedules)
Resources (sufficient resource, skills and capabilities, availability, team motivation)
Project management (PM, BA, tools)
Assumptions
Change
Issues
Stakeholder management
Communications
Suppliers
Effective management and governance (escalation policy, decision making process)
Impact of other projects or programmes
Business impact and readiness for change
Familiarity with project
Date captured
When was this risk identified and captured. Use the format dd/mm/yy.
This document is used all the way through Feasibility, Foundations, Exploration, Engineering and Deployment.
Impact
What is the impact on the project of this risk occurring?
| High | 3
| Medium | 2
| Low | 1
Likelihood
What is the likelihood of the risk occurring?
| Always | 5 | Definitely will happen
| Often | 4 | Highly likely
| Sometimes | 3 | May happen
| Rarely | 2 | Probably won't happy
| Never | 1 | Will not happen
Risk
Calculated automatically: risk = impact × likelihood.
Owner
Each risk needs to have an owner who understands the actions for which they are responsible, in order to manage the risk.
Action required to resolve
Decide on an action for each prioritised risk:
Do nothing, but continue to monitor.
Reduce the likelihood of the risk occurring.
Reduce the exposure of the project to the risk.
Make a contingency plan to deal with the effects of the risk.
In the worst case, if the risk to business is too high and it is not possible to mitigate or avoid the risk, stop the project and determine if there is a different way to achieve your goals.
Resolution due date
Determine the most appropriate time to take action. It may be now; it may be later when a specific event has occurred or you have more information. (However, you have to do it soon enough so that your action will be effective.)
Sources
Agile Project Management Handbook, DSDM Consortium (2013)
Brilliant checklists for Project Managers, Richard Newton (2011)

## Risk log notes
Notes
Ref.
Sequential reference number (unique identifier) so that risks can be referenced. (If you remove risks from the list do not renumber the remaining risks.)
Description
Identify sources of risk. Do not worry when you find risks—project management is largely about risk management.
Project definition (objectives, scope, requirements)
Business case
Budget
Support for the project
Expectations
Plan (estimates, schedules)
Resources (sufficient resource, skills and capabilities, availability, team motivation)
Project management (PM, BA, tools)
Assumptions
Change
Issues
Stakeholder management
Communications
Suppliers
Effective management and governance (escalation policy, decision making process)
Impact of other projects or programmes
Business impact and readiness for change
Familiarity with project
Date captured
When was this risk identified and captured. Use the format dd/mm/yy.
This document is used all the way through Feasibility, Foundations, Exploration, Engineering and Deployment.
Impact
What is the impact on the project of this risk occurring?
High | 3
Medium | 2
Low | 1
Likelihood
What is the likelihood of the risk occurring?
Always | 5 | Definitely will happen
Often | 4 | Highly likely
Sometimes | 3 | May happen
Rarely | 2 | Probably won't happy
Never | 1 | Will not happen
Risk
Calculated automatically: risk = impact × likelihood.
Owner
Each risk needs to have an owner who understands the actions for which they are responsible, in order to manage the risk.
Action required to resolve
Decide on an action for each prioritised risk:
Do nothing, but continue to monitor.
Reduce the likelihood of the risk occurring.
Reduce the exposure of the project to the risk.
Make a contingency plan to deal with the effects of the risk.
In the worst case, if the risk to business is too high and it is not possible to mitigate or avoid the risk, stop the project and determine if there is a different way to achieve your goals.
Resolution due date
Determine the most appropriate time to take action. It may be now; it may be later when a specific event has occurred or you have more information. (However, you have to do it soon enough so that your action will be effective.)
Sources
Agile Project Management Handbook, DSDM Consortium (2013)
Brilliant checklists for Project Managers, Richard Newton (2011)